## Task Planning
Task Planning Farm Life
name | details | size | status | week of 2020 | start time | end time
persistence | → make objects persist from day to day → include position and state | 2 h | open | 19
Shop | → gui in night mode to sell items for money → tracking of items/resources | 1 h | open | 19
Interaction model | → pick whats available, by closest to camera center ray → use outline shader to show selected → display interaction text on interactable | 1h | open | 19
Shop2 | → introduce stations as a concept → Buy and sell goods at shop “station” | 1h | open | 19
Alchemy System | → create system to formulate and execute ‘recipes’ → including “objects”, “resources” , “tools” and “stations” | 1h | open | 19
Farming2 | → prep ground, sow seeds, grow, harvest cycle → with cycle times in float days and effectiveness of action based on skill → add fecundity and water to ground tiles → add different ground types, rock, sand, earth, black earth | 1h | open | 19
Cheat console | → add in game cheat console to affect gamestate | 30 min | open | 19